## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | Software Development | 68 days? | September 11, 2019 8:00 AM | December 13, 2019 5:00 PM |  | 0
1 | Yes | Auto Scheduled | Scope | 5 days | September 11, 2019 8:00 AM | September 17, 2019 5:00 PM |  | 1
2 | Yes | Auto Scheduled | Create scope statement | 3 days | September 11, 2019 8:00 AM | September 13, 2019 5:00 PM |  | 2
3 | Yes | Auto Scheduled | Review scope | 1 day | September 16, 2019 8:00 AM | September 16, 2019 5:00 PM | 2 | 2
4 | Yes | Auto Scheduled | Secure project approval | 1 day | September 17, 2019 8:00 AM | September 17, 2019 5:00 PM | 3 | 2
5 | Yes | Auto Scheduled | Scope complete | 0 days | September 17, 2019 5:00 PM | September 17, 2019 5:00 PM | 4 | 2
6 | Yes | Auto Scheduled | Analysis/Software Requirements | 10 days | September 18, 2019 8:00 AM | October 1, 2019 5:00 PM |  | 1
7 | Yes | Auto Scheduled | Discuss preliminary requirements | 1 day | September 18, 2019 8:00 AM | September 18, 2019 5:00 PM | 5 | 2
8 | Yes | Auto Scheduled | Draft software requirements | 3 days | September 19, 2019 8:00 AM | September 23, 2019 5:00 PM | 7 | 2
9 | Yes | Auto Scheduled | Review requirements | 1 day | September 24, 2019 8:00 AM | September 24, 2019 5:00 PM | 8 | 2
10 | Yes | Auto Scheduled | Revise requirements | 2 days | September 25, 2019 8:00 AM | September 26, 2019 5:00 PM | 9 | 2
11 | Yes | Auto Scheduled | Build project plan | 3 days | September 27, 2019 8:00 AM | October 1, 2019 5:00 PM | 10 | 2
12 | Yes | Auto Scheduled | Analysis complete | 0 days | October 1, 2019 5:00 PM | October 1, 2019 5:00 PM | 11 | 2
13 | Yes | Manually Scheduled | Sprint 1 Development | 11 days | October 2, 2019 8:00 AM | October 16, 2019 5:00 PM |  | 1
14 | Yes | Auto Scheduled | Review functional specifications | 1 day | October 2, 2019 8:00 AM | October 2, 2019 5:00 PM |  | 2
15 | Yes | Auto Scheduled | Develop architectural diagram | 2 days | October 3, 2019 8:00 AM | October 4, 2019 5:00 PM | 14 | 2
16 | Yes | Auto Scheduled | Development | 6 days | October 7, 2019 8:00 AM | October 14, 2019 5:00 PM | 15 | 2
17 | Yes | Auto Scheduled | Sprint 1 complete | 0 days | October 14, 2019 5:00 PM | October 14, 2019 5:00 PM | 16 | 2
18 | Yes | Manually Scheduled | Sprint 2 Development | 15 days? | October 16, 2019 8:00 AM | November 5, 2019 5:00 PM |  | 1
19 | Yes | Auto Scheduled | Development | 14 days | October 16, 2019 8:00 AM | November 4, 2019 5:00 PM | 17 | 2
20 | Yes | Auto Scheduled | Sprint 3 planning | 1 day | November 5, 2019 8:00 AM | November 5, 2019 5:00 PM | 19 | 2
21 | Yes | Auto Scheduled | Sprint 2 complete | 0 days | November 5, 2019 5:00 PM | November 5, 2019 5:00 PM | 20 | 2
22 | Yes | Manually Scheduled | Sprint 3 development | 20 days? | November 6, 2019 8:00 AM | December 3, 2019 5:00 PM |  | 1
23 | Yes | Auto Scheduled | Development | 16 days | November 6, 2019 8:00 AM | November 27, 2019 5:00 PM | 21 | 2
24 | Yes | Auto Scheduled | Development complete | 0 days | December 2, 2019 8:00 AM | December 2, 2019 8:00 AM | 23 | 2
25 | Yes | Auto Scheduled | Testing | 48 days | October 2, 2019 8:00 AM | December 6, 2019 5:00 PM |  | 1
26 | Yes | Auto Scheduled | Develop unit test plans using product specifications | 4 days | October 2, 2019 8:00 AM | October 7, 2019 5:00 PM | 12 | 2
27 | Yes | Manually Scheduled | Unit Testing | 36 days | October 16, 2019 8:00 AM | December 4, 2019 5:00 PM |  | 2
28 | Yes | Auto Scheduled | Sprint 1 testing | 4 days | October 15, 2019 8:00 AM | October 18, 2019 5:00 PM | 16 | 3
29 | Yes | Auto Scheduled | Sprint 2 testing | 4 days | November 5, 2019 8:00 AM | November 8, 2019 5:00 PM | 19 | 3
30 | Yes | Auto Scheduled | Sprint 3 testing | 3 days | December 2, 2019 8:00 AM | December 4, 2019 5:00 PM | 23 | 3
31 | Yes | Auto Scheduled | Unit testing complete | 0 days | December 4, 2019 5:00 PM | December 4, 2019 5:00 PM | 30 | 3
32 | Yes | Auto Scheduled | Integration Testing | 2 days | December 5, 2019 8:00 AM | December 6, 2019 5:00 PM |  | 2
33 | Yes | Auto Scheduled | Test module integration | 2 days | December 5, 2019 8:00 AM | December 6, 2019 5:00 PM | 31 | 3
34 | Yes | Auto Scheduled | Integration testing complete | 0 days | December 6, 2019 5:00 PM | December 6, 2019 5:00 PM | 33 | 3
35 | Yes | Auto Scheduled | Documentation | 39 days | October 15, 2019 8:00 AM | December 6, 2019 5:00 PM |  | 1
36 | Yes | Manually Scheduled | Write Sprint 1 documentation | 3 days | October 15, 2019 8:00 AM | October 17, 2019 5:00 PM | 17 | 2
37 | Yes | Auto Scheduled | Write Sprint 2 documentation | 3 days | November 5, 2019 8:00 AM | November 7, 2019 5:00 PM | 19 | 2
38 | Yes | Auto Scheduled | Write Sprint 3 documentation | 3 days | December 2, 2019 8:00 AM | December 4, 2019 5:00 PM |  | 2
39 | Yes | Auto Scheduled | Review and Format API documentation | 2 days | December 5, 2019 8:00 AM | December 6, 2019 5:00 PM | 38 | 2
40 | Yes | Auto Scheduled | Documentation complete | 0 days | December 6, 2019 5:00 PM | December 6, 2019 5:00 PM | 39 | 2
41 | Yes | Auto Scheduled | Deployment | 49 days | October 2, 2019 8:00 AM | December 9, 2019 5:00 PM |  | 1
42 | Yes | Auto Scheduled | Determine final deployment strategy | 1 day | October 2, 2019 8:00 AM | October 2, 2019 5:00 PM | 12 | 2
43 | Yes | Auto Scheduled | Develop deployment methodology | 1 day | October 3, 2019 8:00 AM | October 3, 2019 5:00 PM | 42 | 2
44 | Yes | Auto Scheduled | Secure deployment resources | 1 day | October 4, 2019 8:00 AM | October 4, 2019 5:00 PM | 43 | 2
45 | Yes | Auto Scheduled | Deploy software | 1 day | December 9, 2019 8:00 AM | December 9, 2019 5:00 PM | 34 | 2
46 | Yes | Auto Scheduled | Deployment complete | 0 days | December 9, 2019 5:00 PM | December 9, 2019 5:00 PM | 45 | 2
47 | Yes | Auto Scheduled | Post Implementation Review | 4 days | December 10, 2019 8:00 AM | December 13, 2019 5:00 PM |  | 1
48 | Yes | Auto Scheduled | Wait for final grade! | 4 days | December 10, 2019 8:00 AM | December 13, 2019 5:00 PM | 46 | 2
49 | Yes | Auto Scheduled | Post implementation review complete | 0 days | December 13, 2019 5:00 PM | December 13, 2019 5:00 PM | 48 | 2
50 | Yes | Auto Scheduled | Software development template complete | 0 days | December 13, 2019 5:00 PM | December 13, 2019 5:00 PM | 49 | 1

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Management | M | Work |  |  |  |  | 100% | $0.00/h | 0
2 | Brian (Proj Mgr) | B | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Lindsay (Analyst) | L | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Hailey (Dev) | H | Work |  |  |  |  | 100% | $0.00/h | 0
5 | QA Team | Q | Work |  |  |  |  | 100% | $0.00/h | 0
6 | Trainers | T | Work |  |  |  |  | 100% | $0.00/h | 0
7 | Tech Writers | T | Work |  |  |  |  | 100% | $0.00/h | 0
8 | Deployment Team | D | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Create scope statement | Management | 1 | 24h | 100%
Review scope | Management | 1 | 8h | 100%
Secure project approval | Brian (Proj Mgr) | 1 | 8h | 100%
Discuss preliminary requirements | Lindsay (Analyst) | 1 | 8h | 100%
Discuss preliminary requirements | Hailey (Dev) | 1 | 0h | 100%
Discuss preliminary requirements | Brian (Proj Mgr) | 1 | 0h | 100%
Draft software requirements | Lindsay (Analyst) | 1 | 24h | 100%
Review requirements | Brian (Proj Mgr) | 1 | 8h | 100%
Review requirements | Lindsay (Analyst) | 1 | 8h | 100%
Revise requirements | Lindsay (Analyst) | 1 | 16h | 100%
Build project plan | Brian (Proj Mgr) | 1 | 24h | 100%
Review functional specifications | Hailey (Dev) | 0 | 8h | 100%
Develop architectural diagram | Hailey (Dev) | 0 | 16h | 100%
Development | Hailey (Dev) | 0 | 48h | 100%
Development | Hailey (Dev) | 0 | 112h | 100%
Development | Hailey (Dev) | 0 | 128h | 100%
Develop unit test plans using product specifications | QA Team | 0 | 32h | 100%
Sprint 1 testing | QA Team | 0 | 32h | 100%
Sprint 2 testing | QA Team | 0 | 32h | 100%
Sprint 3 testing | QA Team | 0 | 24h | 100%
Test module integration | QA Team | 0 | 16h | 100%
Write Sprint 1 documentation | Tech Writers | 0 | 24h | 100%
Write Sprint 2 documentation | Tech Writers | 0 | 24h | 100%
Review and Format API documentation | Tech Writers | 0 | 16h | 100%
Determine final deployment strategy | Deployment Team | 1 | 8h | 100%
Develop deployment methodology | Deployment Team | 1 | 8h | 100%
Secure deployment resources | Deployment Team | 1 | 8h | 100%
Deploy software | Deployment Team | 0 | 8h | 100%
Wait for final grade! | Brian (Proj Mgr) | 0 | 32h | 100%