## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | Software Development | 86.75 days? | September 11, 2019 8:00 AM | January 9, 2020 3:00 PM |  | 0
1 | Yes | Auto Scheduled | Scope | 5 days | September 11, 2019 8:00 AM | September 17, 2019 5:00 PM |  | 1
2 | Yes | Auto Scheduled | Create scope statement | 3 days | September 11, 2019 8:00 AM | September 13, 2019 5:00 PM |  | 2
3 | Yes | Auto Scheduled | Review scope | 1 day | September 16, 2019 8:00 AM | September 16, 2019 5:00 PM | 2 | 2
4 | Yes | Auto Scheduled | Secure project approval | 1 day | September 17, 2019 8:00 AM | September 17, 2019 5:00 PM | 3 | 2
5 | Yes | Auto Scheduled | Scope complete | 0 days | September 17, 2019 5:00 PM | September 17, 2019 5:00 PM | 4 | 2
6 | Yes | Auto Scheduled | Analysis/Software Requirements | 10 days | September 18, 2019 8:00 AM | October 1, 2019 5:00 PM |  | 1
7 | Yes | Auto Scheduled | Discuss preliminary requirements | 1 day | September 18, 2019 8:00 AM | September 18, 2019 5:00 PM | 5 | 2
8 | Yes | Auto Scheduled | Draft software requirements | 3 days | September 19, 2019 8:00 AM | September 23, 2019 5:00 PM | 7 | 2
9 | Yes | Auto Scheduled | Review requirements | 1 day | September 24, 2019 8:00 AM | September 24, 2019 5:00 PM | 8 | 2
10 | Yes | Auto Scheduled | Revise requirements | 2 days | September 25, 2019 8:00 AM | September 26, 2019 5:00 PM | 9 | 2
11 | Yes | Auto Scheduled | Build project plan | 3 days | September 27, 2019 8:00 AM | October 1, 2019 5:00 PM | 10 | 2
12 | Yes | Auto Scheduled | Analysis complete | 0 days | October 1, 2019 5:00 PM | October 1, 2019 5:00 PM | 11 | 2
13 | Yes | Manually Scheduled | Sprint 1 Development | 11 days | October 2, 2019 8:00 AM | October 16, 2019 5:00 PM |  | 1
14 | Yes | Auto Scheduled | Review functional specifications | 1 day | October 2, 2019 8:00 AM | October 2, 2019 5:00 PM |  | 2
15 | Yes | Auto Scheduled | Develop architectural diagram | 2 days | October 3, 2019 8:00 AM | October 4, 2019 5:00 PM | 14 | 2
16 | Yes | Auto Scheduled | Development | 6 days | October 7, 2019 8:00 AM | October 14, 2019 5:00 PM | 15 | 2
17 | Yes | Auto Scheduled | Dev testing | 5 days | October 8, 2019 1:00 PM | October 15, 2019 12:00 PM | 16FS-75% | 2
18 | Yes | Auto Scheduled | Sprint 1 complete | 0 days | October 15, 2019 12:00 PM | October 15, 2019 12:00 PM | 17 | 2
19 | Yes | Manually Scheduled | Sprint 2 Development | 15 days | October 16, 2019 8:00 AM | November 5, 2019 5:00 PM |  | 1
20 | Yes | Auto Scheduled | Development | 14 days | October 16, 2019 8:00 AM | November 4, 2019 5:00 PM | 18 | 2
21 | Yes | Auto Scheduled | Dev testing | 11 days | October 21, 2019 1:00 PM | November 5, 2019 12:00 PM | 20FS-75% | 2
22 | Yes | Auto Scheduled | Sprint 2 complete | 0 days | November 5, 2019 12:00 PM | November 5, 2019 12:00 PM | 21 | 2
23 | Yes | Manually Scheduled | Sprint 3 development | 20 days? | November 6, 2019 8:00 AM | December 3, 2019 5:00 PM |  | 1
24 | Yes | Auto Scheduled | Development | 19 days | November 6, 2019 8:00 AM | December 2, 2019 5:00 PM | 22 | 2
25 | Yes | Manually Scheduled | Dev testing | 15 days | November 12, 2019 3:00 PM | December 3, 2019 3:00 PM | 24FS-75% | 2
26 | Yes | Auto Scheduled | Development complete | 0 days | December 3, 2019 3:00 PM | December 3, 2019 3:00 PM | 25 | 2
27 | Yes | Auto Scheduled | Testing | 71.75 days | October 2, 2019 8:00 AM | January 9, 2020 3:00 PM |  | 1
28 | Yes | Auto Scheduled | Develop unit test plans using product specifications | 4 days | October 2, 2019 8:00 AM | October 7, 2019 5:00 PM | 12 | 2
29 | Yes | Auto Scheduled | Unit Testing | 15 days | December 3, 2019 3:00 PM | December 24, 2019 3:00 PM |  | 2
30 | Yes | Auto Scheduled | Review modular code | 5 days | December 3, 2019 3:00 PM | December 10, 2019 3:00 PM | 28,26 | 3
31 | Yes | Auto Scheduled | Test component modules to product specifications | 2 days | December 10, 2019 3:00 PM | December 12, 2019 3:00 PM | 26,30 | 3
32 | Yes | Auto Scheduled | Identify anomalies to product specifications | 3 days | December 12, 2019 3:00 PM | December 17, 2019 3:00 PM | 31 | 3
33 | Yes | Auto Scheduled | Modify code | 3 days | December 17, 2019 3:00 PM | December 20, 2019 3:00 PM | 32 | 3
34 | Yes | Auto Scheduled | Re-test modified code | 2 days | December 20, 2019 3:00 PM | December 24, 2019 3:00 PM | 33 | 3
35 | Yes | Auto Scheduled | Unit testing complete | 0 days | December 24, 2019 3:00 PM | December 24, 2019 3:00 PM | 34 | 3
36 | Yes | Auto Scheduled | Integration Testing | 12 days | December 24, 2019 3:00 PM | January 9, 2020 3:00 PM |  | 2
37 | Yes | Auto Scheduled | Test module integration | 5 days | December 24, 2019 3:00 PM | December 31, 2019 3:00 PM | 35 | 3
38 | Yes | Auto Scheduled | Identify anomalies to specifications | 2 days | December 31, 2019 3:00 PM | January 2, 2020 3:00 PM | 37 | 3
39 | Yes | Auto Scheduled | Modify code | 3 days | January 2, 2020 3:00 PM | January 7, 2020 3:00 PM | 38 | 3
40 | Yes | Auto Scheduled | Re-test modified code | 2 days | January 7, 2020 3:00 PM | January 9, 2020 3:00 PM | 39 | 3
41 | Yes | Auto Scheduled | Integration testing complete | 0 days | January 9, 2020 3:00 PM | January 9, 2020 3:00 PM | 40 | 3
42 | Yes | Auto Scheduled | Documentation | 41 days | September 11, 2019 8:00 AM | November 6, 2019 5:00 PM |  | 1
43 | Yes | Auto Scheduled | Develop Help specification | 1 day | September 11, 2019 8:00 AM | September 11, 2019 5:00 PM |  | 2
44 | Yes | Auto Scheduled | Develop Help system | 3 wks | October 10, 2019 8:00 AM | October 30, 2019 5:00 PM | 43,16FS-50% | 2
45 | Yes | Auto Scheduled | Review Help documentation | 3 days | October 31, 2019 8:00 AM | November 4, 2019 5:00 PM | 44 | 2
46 | Yes | Auto Scheduled | Incorporate Help documentation feedback | 2 days | November 5, 2019 8:00 AM | November 6, 2019 5:00 PM | 45 | 2
47 | Yes | Auto Scheduled | Develop user manuals specifications | 2 days | September 11, 2019 8:00 AM | September 12, 2019 5:00 PM |  | 2
48 | Yes | Auto Scheduled | Develop user manuals | 3 wks | October 10, 2019 8:00 AM | October 30, 2019 5:00 PM | 47,16FS-50% | 2
49 | Yes | Auto Scheduled | Review all user documentation | 2 days | October 31, 2019 8:00 AM | November 1, 2019 5:00 PM | 48 | 2
50 | Yes | Auto Scheduled | Incorporate user documentation feedback | 2 days | November 4, 2019 8:00 AM | November 5, 2019 5:00 PM | 49 | 2
51 | Yes | Auto Scheduled | Documentation complete | 0 days | November 6, 2019 5:00 PM | November 6, 2019 5:00 PM | 50,46 | 2
52 | Yes | Auto Scheduled | Deployment | 5 days | September 11, 2019 8:00 AM | September 17, 2019 5:00 PM |  | 1
53 | Yes | Auto Scheduled | Determine final deployment strategy | 1 day | September 11, 2019 8:00 AM | September 11, 2019 5:00 PM |  | 2
54 | Yes | Auto Scheduled | Develop deployment methodology | 1 day | September 12, 2019 8:00 AM | September 12, 2019 5:00 PM | 53 | 2
55 | Yes | Auto Scheduled | Secure deployment resources | 1 day | September 13, 2019 8:00 AM | September 13, 2019 5:00 PM | 54 | 2
56 | Yes | Auto Scheduled | Train support staff | 1 day | September 16, 2019 8:00 AM | September 16, 2019 5:00 PM | 55 | 2
57 | Yes | Auto Scheduled | Deploy software | 1 day | September 17, 2019 8:00 AM | September 17, 2019 5:00 PM | 56 | 2
58 | Yes | Auto Scheduled | Deployment complete | 0 days | September 17, 2019 5:00 PM | September 17, 2019 5:00 PM | 57 | 2
59 | Yes | Auto Scheduled | Post Implementation Review | 3 days | September 18, 2019 8:00 AM | September 20, 2019 5:00 PM |  | 1
60 | Yes | Auto Scheduled | Document lessons learned | 1 day | September 18, 2019 8:00 AM | September 18, 2019 5:00 PM | 58 | 2
61 | Yes | Auto Scheduled | Distribute to team members | 1 day | September 19, 2019 8:00 AM | September 19, 2019 5:00 PM | 60 | 2
62 | Yes | Auto Scheduled | Create software maintenance team | 1 day | September 20, 2019 8:00 AM | September 20, 2019 5:00 PM | 61 | 2
63 | Yes | Auto Scheduled | Post implementation review complete | 0 days | September 20, 2019 5:00 PM | September 20, 2019 5:00 PM | 62 | 2
64 | Yes | Auto Scheduled | Software development template complete | 0 days | September 20, 2019 5:00 PM | September 20, 2019 5:00 PM | 63 | 1

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Management | M | Work |  |  |  |  | 100% | $0.00/h | 0
2 | Project Manager | P | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Analyst | A | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Developer | D | Work |  |  |  |  | 100% | $0.00/h | 0
5 | Testers | T | Work |  |  |  |  | 100% | $0.00/h | 0
6 | Trainers | T | Work |  |  |  |  | 100% | $0.00/h | 0
7 | Technical Communicators | T | Work |  |  |  |  | 100% | $0.00/h | 0
8 | Deployment Team | D | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Create scope statement | Management | 1 | 24h | 100%
Review scope | Management | 1 | 8h | 100%
Secure project approval | Project Manager | 1 | 8h | 100%
Discuss preliminary requirements | Analyst | 1 | 8h | 100%
Discuss preliminary requirements | Developer | 1 | 0h | 100%
Discuss preliminary requirements | Project Manager | 1 | 0h | 100%
Draft software requirements | Analyst | 1 | 24h | 100%
Review requirements | Project Manager | 1 | 8h | 100%
Review requirements | Analyst | 1 | 8h | 100%
Revise requirements | Analyst | 1 | 16h | 100%
Build project plan | Project Manager | 0.5 | 24h | 100%
Review functional specifications | Developer | 0 | 8h | 100%
Develop architectural diagram | Developer | 0 | 16h | 100%
Development | Developer | 0 | 48h | 100%
Dev testing | Developer | 0 | 33.33h | 83%
Development | Developer | 0 | 112h | 100%
Dev testing | Developer | 0 | 88h | 100%
Development | Developer | 0 | 152h | 100%
Dev testing | Developer | 0 | 120h | 100%
Develop unit test plans using product specifications | Testers | 0 | 32h | 100%
Review modular code | Testers | 0 | 40h | 100%
Test component modules to product specifications | Testers | 0 | 16h | 100%
Identify anomalies to product specifications | Testers | 0 | 24h | 100%
Modify code | Testers | 0 | 24h | 100%
Re-test modified code | Testers | 0 | 16h | 100%
Test module integration | Testers | 0 | 40h | 100%
Identify anomalies to specifications | Testers | 0 | 16h | 100%
Modify code | Testers | 0 | 24h | 100%
Re-test modified code | Testers | 0 | 16h | 100%
Develop Help specification | Technical Communicators | 0 | 8h | 100%
Develop Help system | Technical Communicators | 0 | 120h | 100%
Review Help documentation | Technical Communicators | 0 | 24h | 100%
Incorporate Help documentation feedback | Technical Communicators | 0 | 16h | 100%
Develop user manuals specifications | Technical Communicators | 0 | 16h | 100%
Develop user manuals | Technical Communicators | 0 | 120h | 100%
Review all user documentation | Technical Communicators | 0 | 16h | 100%
Incorporate user documentation feedback | Technical Communicators | 0 | 16h | 100%
Determine final deployment strategy | Deployment Team | 0 | 8h | 100%
Develop deployment methodology | Deployment Team | 0 | 8h | 100%
Secure deployment resources | Deployment Team | 0 | 8h | 100%
Train support staff | Deployment Team | 0 | 8h | 100%
Deploy software | Deployment Team | 0 | 8h | 100%
Document lessons learned | Project Manager | 0 | 8h | 100%
Distribute to team members | Project Manager | 0 | 8h | 100%
Create software maintenance team | Project Manager | 0 | 8h | 100%